Risk Register

| Risk ID | Risk Name | Description | Likelihood | Impact | Mitigation Strategy |
| --- | --- | --- | --- | --- | --- |
| R1 | Client Misalignment & Missing Feedback | Inconsistent meetings or poor communication with the client may lead to wrong assumptions about project requirements. | Medium | High | Establish recurring meeting schedules early. Copy all team members on emails to keep everyone in the loop & use Teams and Discord for everyday communication between team members. |
| R2 | Architecture Delay – No Existing recording tool | Because there is no existing version of the app to reference, the team may waste time figuring out how to build the structure from scratch. | Medium | Medium | Research existing manual recording tools and use open-source 2D SVG rendering examples |
| R3 | Unrealistic Project Scope (Scope Creep) | Setting over-ambitious goals (e.g., trying to support child/adolescent SVGs immediately) can lead to an unfinished project. | High | High | Set a MVP boundary early in the process which means focus only on adult skeletons |
| R4 | SVG Zonation | Splitting the skeleton into interactive “bone zones” is highly time-consuming and can delay coding. | High | High | Assign high priority to Zonation and start preparation early |
| R5 | Skills Gap | Limited software development skills within the team can delay implementation | Medium | High | Assign project roles based on current abilities. Where necessary, skills are learnt before development starts. |
| R6 | Database & SVG Naming Mismatch | The database schema designed does not match the IDs used by the SVG designer, causing data errors. | Medium | Medium | Create a shared “Naming Convention” document (e.g., in GitHub) that both the SVG designer and database coder must follow. |
| R7 | CSV Export/Import Failures | Issues writing the parser could result in the application failing to export valid CSVs or failing to read imported CSVs. | Medium | High | Design the CSV schema first. Write simple, isolated JavaScript validation utility functions to test importing and exporting before integrating with the DB. |
| R8 | Device UI Layout Distortion | Varying phone screen sizes can cause browser address bars to stretch the skeleton aspect ratio or push controls off-screen. | High | Medium | Contain the SVG inside fixed aspect ratio parent wrappers |
| R9 | Touchscreen & Zoom Usability Lag | Pan and zoom functionality works well on desktop browsers but is laggy or unresponsive on small mobile screens. | Medium | Medium | Possibly implement click-to-zoom as a backup mechanism for smaller bones in hands and feet, rather than relying on pinch-to-zoom. |
| R10 | Local Storage Quotas & Unexpected Deletion | Mobile browsers enforce strict storage quotas and automatically clear IndexedDB under disk pressure, causing permanent data loss. | High | High | Emphasize that CSV exports are the primary permanent backup. |
| R11 | Lack of Baseline for Verification | No existing app to compare functionality against makes it hard to verify if the app runs correctly. | Medium | Medium | Create a thorough testing plan combining Unit Tests, Integration Tests, System Tests, and User Acceptance Tests. |
| R12 | High Application Complexity | The client and users find the app interface too difficult to use. | Medium | High | Keep the user interface (UI) as simple and intuitive as possible. Allow the client to test the app before deployment |
| R13 | Team Communication Breakdown | Missed updates or misalignment on code integration can stall team momentum. | Medium | High | Use Discord for daily quick updates, CC for all emails and weekly meetings. |
| R14 | Timesheet Submission Penalties | Team members delaying submission of Booked Hours | High | Medium | Agree on a deadline to allow Project Manager enough time to gather all necessary details and update Spreadsheet |
| R15 | Imbalanced Technical Contribution | One or two members doing all the heavy coding, leading to potential exhaustion and unattended tasks. | Medium | High | Divide development tasks amongst team members. Assigning Project Manager to everyone at least once throughout the course of the Semester |